## Annex 10.4 Evaluability study

The analysis of the evaluability of the South-West Oltenia Regional Programme 2021-2027 represents an essential preliminary stage for establishing the feasibility of evaluating the programme interventions, also fulfilling the role of a mechanism for identifying possible obstacles or methodological limitations that could prevent an efficient and relevant evaluation. According to the Evalsed Guide, the analysis of evaluability involves examining the coherence and logic of the programme, evaluating the availability of data, and analyzing the extent to which managers or stakeholders could use the results of the evaluation, considering their usefulness and relevance in decision-making processes.

The main purpose of the evaluation analysis is to investigate the intervention logic, i.e. the assumptions, the planned mechanisms and the expected results of the programme. It also assesses the extent to which the programme can achieve the policy objectives or priorities for which it was designed. Another important aspect is the analysis of the availability of the necessary information, including data from primary and secondary sources, the difficulty of accessing them and the possible challenges in cooperation with the key actors that will have to be involved in this process.

The analysis of the evaluability of the South-West Oltenia RP 2021-2027 is carried out through a qualitative approach, which considers the specifics of the programme interventions, the main relevant strategic and programming documents and the data from the programme monitoring system.

Criteria for the evaluability

The criteria used to analyze and test the programme's evaluability are as follows:

- Coherence of the intervention logic, which looks at the existence of a clear and logical relationship between the different components of the programme, such as activities, resources and expected results. A well-structured intervention should reflect how each activity contributes to the achievement of specific objectives.

- The relevance of the evaluation, which analyzes the progress of the implementation of the interventions at the level of each priority of the programme and the extent to which it is sufficient to obtain relevant and comprehensive findings and conclusions regarding the effects of the interventions.

- Data independence and completeness. By applying this criterion, evaluators ensure that the data available for evaluation are objective and complete, so as to minimize bias and allow for the most comprehensive analysis of the programme.

- Measurability of interventions for each specific priority and objective. Interventions must be formulated in such a way that they can be measured by specific indicators, which allow the evaluation of the progress of the programme.

These criteria were translated into a 'checklist' divided into three main sections (see the grid below): 1) reliability, flexibility and responsiveness of the intervention logic; 2) the possibility of checking the results obtained; 3) feasibility, credibility and usefulness of the evaluation process. Each question/ item is then assessed based on qualitative criteria (low/medium/high).

The results of the analysis of the evaluability of SW Oltenia RP 2021-2027 are transposed into the following table:

| Questions |  | Level of evaluability |
| --- | --- | --- |
| Is the intervention logic reliable, flexible and responsive? | Is the justification of the intervention realistic? |  |
|  | Is the logframe flexible and responsive to external factors? |  |
|  | Are the objectives of the programme clear, realistic and commonly understood by the stakeholders? |  |
| Are the results verifiable? | Are the output and result indicators available? Are the indicators adequately monitored? |  |
|  | Are baseline data available to track change? |  |
|  | Is monitoring data planned to be collected on a regular basis against the indicators? |  |
|  | Does the present stage of the execution of the programme allows for evaluation? |  |
| Is the evaluation credible and useful? | Does the timing of the evaluation fit into the programme cycle (usefulness of evaluation at that point in time)? |  |
|  | Have the priorities of the programme been previously evaluated? |  |
|  | Are key stakeholders available to participate in data collection activities during the planned evaluation period? |  |

Legend: Low, Medium, High

Reliability, flexibility and responsiveness of intervention logic

In general, the intervention logic of the South-West Oltenia Regional Programme 2021-2027 can be considered reliable, as it is based on a solid analysis of the needs at the regional level and on a well-founded strategic planning. The interventions selected within the 8 priorities of the programme are adequately and comprehensively justified by analyzes of the relevant statistical indicators for each specific objective. The difficulties, challenges and socio-economic needs of the region are developed on the basis of an analysis exercise that includes, in addition to regional or local statistical data, evidence of problems or deficiencies captured in the main strategic documents and sectoral public policy documents developed at the national or European level. The context analysis and presentation of needs is thus well documented, and the interventions proposed in the programme respond to concrete problems and clearly defined priorities of the region.

The logical framework of the programme was designed in such a way that it could integrate the necessary changes and adjustments depending on the influence of endogenous factors, such as the attractiveness and success of the planned interventions, or exogenous factors, such as the dynamics of territorial needs and the regional context or possible legislative, economic and social changes, which may influence the expected results. The premises for the flexibility of the programme are ensured, first of all, through the evaluations established at the level of the South-West Oltenia RP Evaluation Plan 2021-2027, including through this mid-term evaluation, which will analyze the coherence and relevance of the programmed and implemented actions, as well as the efficiency or the impact of the programme, facilitating the adoption of possible adjustments, if necessary. The mid-term evaluation will confirm whether the start of the implementation of the programme is according to the expectations and will identify any deviations from them, with a view to taking corrective measures, if necessary, including proposals regarding the definitive allocation of the flexibility amount or proposals to modify the programme, where these are highlighted.

An eminently participatory process, the evaluation will allow the creation of feedback mechanisms through activities related to data collection and consultation of interested parties (interviews, surveys,  panel of experts, focus groups etc.), within which opinions, suggestions and comments on programme implementation and factors that determined the success or failure of interventions will be collected. These feedback mechanisms are crucial not only for adjusting the measures already implemented, but also for identifying best practices that can be replicated in the next stages of the program. They also facilitate the decision-making process, providing direct information from program beneficiaries and other stakeholders. In this way, evaluation is not limited to a mere analysis of data, but becomes a continuous process of improving and adapting the program, thus contributing to the success of its implementation.

Possibility of verifying the results obtained

The SW Oltenia RP was approved in October 2022, which led to a time gap between the official start of the programming period (2021) and the actual launch of the first calls for projects, which were initiated in June 2023. This gap had a direct impact on the initial planning and implementation of the projects foreseen under the programme.

The schedule of calls for projects was also influenced by the adoption of Emergency Ordinance No. 23 of 12 April 2023 by the Romanian Government, which introduced measures to simplify and digitize the management of European funds related to the 2021-2027 Cohesion Policy. Although these measures were mainly aimed at improving the efficiency of fund management, they imposed additional obligations both for the managing authorities, who were required to transpose the measures provided for in the ordinance, and for the beneficiaries, determining the need to adapt the applicant's guides and the evaluation and contracting procedures.

The South-West Oltenia Regional Programme has made significant progress in launching calls for projects and contracting them, with a total of 36 calls opened by the end of 2024. However, progress in terms of making payments and achieving European and national policy objectives has been slower. However, given the current state of contracted projects, most priorities have significant potential to meet the proposed targets for 2029, at the level of the output and result indicators foreseen in the programme. The only exceptions are the risk of not achieving the indicators in the case of SO 1.2 and SO 2.7, the situation of which is presented below and for which corrective measures are proposed.

The main achievements, achieved across the entire programme, aim to:

- Calls for projects: 36 (including calls for territorial strategies) calls for projects were launched across the entire programme, representing over 1 billion Euros or 80% of the total financial allocation of the programme.

- Contracting: the eligible value of signed contracts of 751 million Euros, which corresponds to over 60% of the total budget allocated to the programme.

- Payments made: payments were made in the amount of 22,084,112.39 Euros (ERDF+SB), representing only 5% of the non-reimbursable value of the contracted projects.

It is also noted that for certain priorities there was a significantly higher interest from beneficiaries, according to the total non-reimbursable values ​​of the projects submitted under the various calls, in particular for Priorities 1, 4, 5 and 7. In contrast, for Priorities 2, 3, 6 and 8, the initial financial allocations were not fully used by the projects submitted. However, it is important to note that, at the time of writing this report, there are open calls for certain specific objectives, which suggests a possible increase in the number of projects submitted and contracted; the specific objectives at which risks have been identified regarding the absorption of the financial allocation are SO 1.2 and SO 2.7.

The contracting stage of the projects, at the level of priority and specific objective, on 31.12.2024 is presented in the table below:

| Priority | SO | No. of submitted projects | No. of rejected projects | No. of projects under evaluation | No. of approved projects | No of projects in pre-contracting | No. of contracted projects | Payments to beneficiaries |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| P1 | SO 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | Nu |
|  | SO 1.3 | 563 | 78 | 0 | 397 | 36 | 52 | Nu |
|  | SO 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | Nu |
| P2 | SO 1.2 | 100 | 11 | 38 | 28 | 19 | 4 | Da |
| P3 | SO 2.1 | 86 | 10 | 0 | 0 | 0 | 76 | Da |
|  | SO 2.7 | 18 | 1 | 3 | 3 | 2 | 9 | Nu |
| P4 | SO 2.8 | 32 | 4 | 6 | 5 | 1 | 16 | Da |
| P5 | SO 3.2 | 9 | 0 | 0 | 0 | 0 | 9 | Da |
| P6 | SO 4.2 | 46 | 2 | 0 | 0 | 0 | 44 | Da |
| P7 | SO 5.1 | 74 | 9 | 9 | 16 | 4 | 36 | Da |
|  | SO 5.2 | 1 | 0 | 0 | 0 | 0 | 1 | Da |
| P8 | TA | 3 | 0 | 1 | 0 | 0 | 2 | Da |
| Total |  | 932 | 115 | 57 | 449 | 62 | 249 | - |

At programme level, calls for proposal were launched for all specific objectives, less within priority 1 (SO 1.1 and SO 1.4), and contracts have already been signed at the level of all investment priorities. Moreover, for the analysis of the evaluability of the different SOs, the projects approved and expected to be contracted in the next period can also be considered. In addition, at the level of certain SOs, it is not necessarily the number of projects that is relevant, but also their scale/complexity (in terms of their importance and value). In addition, it is noted how certain SOs already involve payments made to beneficiaries, which determines that some of the results could already be quantified.

Thus, from the perspective of the number of projects and the application of different research methods on the field, the evaluation can be carried out at the level of all priorities, the application of interviews, case studies and the survey being established for all priorities.

On the other hand, the output and result indicators indicate zero values at the programme level (as reported in December 2024), due to the relatively early stage of implementation of the interventions, which represents a limitation in the evaluation process. On the other hand, the monitoring of the degree of achievement of these indicators is constantly carried out by the Management Authority, according to the monitoring framework, which indicates the possibility of recording progress in the next period. Regarding the existence of the reference data, on the basis of which the planning of the programme was carried out, they can be found both in the programming documents and at the level of the various specialized studies carried out for the South-West Oltenia region (e.g. the Regional Strategy for Intelligent Specialization RIS3).

The current stage of implementation of the SW RP allows for a partial assessment in terms of effects, impact and contribution to the CSR, PNIESC and EPSR. By the end of 2024, a significant number of calls for projects (36) had been launched, for almost all SOs, with numerous projects submitted and projects already contracted, but their implementation stage is still in its early stages. Furthermore, it is important to note that, in terms of implementation, progress has been generally slower. Risks of non-achievement of specific indicators have also been identified (in particular for SO 1.2, 1.3 and 2.7), suggesting that the evaluation needs to take these challenges into account and include corrective measures to ensure that the targets set are met. Therefore, while the evaluation can be carried out at this stage, it needs to be accompanied by a detailed analysis of the state of implementation and associated risks, in order to provide relevant recommendations and adjustments for the next programme period.

Feasibility, credibility and usefulness of the evaluation process

The mid-term evaluation supports compliance with the provisions of art. 18 of Regulation 2021/1060, according to which the Management Authorities have the obligation to prepare such an evaluation and to report the results to the European Commission by March 31, 2025. It should be noted that the mid-term evaluation represents the first evaluation exercise started at the level of the South West Oltenia  Regional Programme 2021-2027, there being no previous similar analyzes except for environmental assessments (strategic environmental assessment and appropriate assessment).

The mid-term evaluation is carried out at a strategic stage in the life cycle of the programme, presenting the advantage of allowing adjustment, adaptation or correction of deviations in an early phase of implementation. At the same time, the substantiation analyzes of the programme were carried out over two years ago, which is why it is necessary to reanalyze the socio-economic situation of the region, taking into account any major negative financial, economic or social evolution or demographic challenges, as well as of the possible progress made towards reaching certain targets (e.g. related to the environment and climate).

Stakeholder availability is essential to gather data for evaluation and to gain a comprehensive perspective on programme implementation. Through its participatory nature, the research aims to involve the interested parties of the program, such as representatives of MA South-West Oltenia RP, project beneficiaries or sector experts, who will provide key information on the programme's operating mechanisms, how it is perceived at the community level and its impact at the regional level. Key actors will be directly involved in the process of collecting and analyzing the information needed for the research process and will be consulted ensuring the participatory and partnership process as well as the transparency of the evaluation exercise.

Data collection activities were designed by the evaluators based on the premise of key actors' availability and openness to dialogue and engagement. However, the unavailability of certain respondents (e.g. the beneficiaries of the interventions) was considered in the context of the registration of a limited number of contracted projects, which is why the evaluators proposed an extended set of research methods to fill in any informational gaps.

European Commission, Directorate-General for Regional and Urban Policy, EVALSED: Resource for evaluating socio-economic development, 2018, link