## Annex 10.6 Survey analysis report

- Beneficiary organization / institution

| Dolj County ATU | 2 |
| --- | --- |
| Vâlcea County ATU | 4 |
| Mehedinți County ATU | 5 |
| Târgu Jiu Municipality ATU | 1 |
| Craiova Municipality ATU | 4 |
| Slatina Municipality ATU | 2 |
| Drobeta Turnu Severin Municipality ATU | 1 |
| Balș City ATU | 1 |
| Turceni City ATU | 1 |
| Ocnele Mari City ATU | 1 |
| Horezu City ATU | 1 |
| Corabia City ATU | 2 |
| Novaci City ATU | 1 |
| PĂUŞEŞTI-MĂGLAŞI Commune ATU | 1 |
| BERISLAVESTI Community ATU | 1 |
| Giubega Commune ATU | 1 |
| COMMUNITY BOAT ATU | 1 |
| BICYCLES Community ATU | 1 |
| Goleşti ATU Community | 1 |
| MALOVĂȚ Commune ATU | 1 |
| Breznita-Detour ATU Community | 1 |
| Galicia Mare Commune ATU | 2 |
| Maglavite ATU Community | 1 |
| University of Medicine and Pharmacy of Craiova | 1 |
| University of Craiova | 2 |
| Romanian Intelligence Service through Military Unit 0929 Bucharest | 1 |
| Inspectorate for Emergency Situations " Oltenia " of Dolj County | 1 |
| Filisanilor Hospital | 1 |

- Your role within the beneficiary organization/institution

| Advisor/Senior Advisor | 12 |
| --- | --- |
| Public procurement advisor | 6 |
| Inspector | 10 |
| Technical manager | 1 |
| Project manager | 5 |
| Service manager | 3 |
| Executive Director | 1 |
| Pro-rector | 1 |
| Mayor | 3 |

- Under which priority of the South-West Oltenia Regional Programme 2021–2027 did your project receive funding?

| Priority P3. Energy efficiency and green infrastructure | 21 | 47.73% |
| --- | --- | --- |
| Priority P6. Modern and inclusive education | 11 | 25.00% |
| Priority P5. Accessibility and connectivity at regional level | 5 | 11.36% |
| Priority P4. Sustainable urban mobility | 4 | 9.09% |
| Priority P7. Sustainable territorial development | 2 | 4.55% |
| Priority P2. Digitalization for the benefit of citizens and businesses | 1 | 2.27% |
| Total | 44 | 100% |

- Have you benefited from other non-reimbursable funding in the last 5 years?

| YES | 43 | 97.7% |
| --- | --- | --- |
| NO | 1 | 2.3% |
| Total | 44 | 100% |

The majority of respondents (97.7%) confirmed that they had accessed other non-reimbursable funding sources in the past five years, demonstrating both a high level of interest among the consulted organizations/institutions in attracting such types of funding and the experience they have acquired in this area.

- Did you use a consultant to prepare the funding application?

| YES | 24 | 54.5% |
| --- | --- | --- |
| NO | 20 | 45.5% |
| Total | 44 | 100% |

The majority of respondents (54.5%) used the services of a consultant to prepare their funding application, indicating that a considerable proportion considered external consultancy necessary to ensure compliance and the quality of the documentation. Conversely, 45.5% of respondents did not use a consultant, suggesting that a significant share managed the application preparation process internally—possibly reflecting sufficient in-house capacity or a strategy based on using internal resources. This distribution points to a diversity of approaches among respondents, with the differences between those who relied on consultancy and those who did not potentially, reflecting variations in available resources as well as differing levels of project complexity.

- Were you involved in the consultation process organized by RDA to define the call for proposals?

| YES | 27 | 61.4% |
| --- | --- | --- |
| NO | 17 | 38.6% |
| Total | 44 | 100% |

The majority of respondents (61.4%) reported being involved in the consultation process, indicating a significant level of participation and an active interest in contributing to the design of the calls for proposals.

- If you answered "Yes" to the previous question, please mention what your involvement consisted of:

| Participation in meetings organized by the RDA for finalizing the applicant guidelines | 22 |
| --- | --- |
| Submission of questions/feedback in writing to RDA | 17 |
| Participation in meetings with other key regional stakeholders to identify needs | 9 |
| Participation in meetings with other key regional stakeholders to establish intervention priorities | 7 |

Participation in the meetings organized by the RDA for finalizing the applicant guidelines was the most common form of beneficiary involvement. Additionally, a significant number of respondents contributed to the consultation process by submitting questions and opinions in writing to RDA.

- What is the need covered by your project?

The projects indicated by the respondents within the survey address a variety of needs and objectives related to the development of intermodal transport infrastructure, energy efficiency and sustainability, improvement of educational infrastructure, rehabilitation of healthcare infrastructure, environmental protection, and green infrastructure, among others.

- How has the need covered by your project evolved in recent years?

| The need identified at the time of project submission has become more acute in recent years | 29 | 67.4% |
| --- | --- | --- |
| The need identified at the time of project submission has improved in recent years | 7 | 16.3% |
| No evolution | 7 | 16.3% |
| Total | 43 | 100% |

The majority of beneficiaries (67.4%) believe that the needs identified at the time of project submission have become more pressing in recent years. The responses indicate that the initial challenges are now more urgent, and the issues addressed by the projects are increasingly relevant.

- How did you find out about this funding opportunity?

| Programme website | 28 |
| --- | --- |
| Communication initiatives organized by the Regional Development Agency | 28 |
| Consultant | 4 |
| Other organizations | 1 |

The most frequently used sources of information by beneficiaries are the programme website and communication initiatives organized by the SW RDA .

- How do you rate the funding application process?

| Very easy | 10 | 22.7% |
| --- | --- | --- |
| Somewhat difficult | 6 | 13.6% |
| Somewhat easy | 28 | 63.6% |
| Total | 44 | 100% |

The majority of beneficiaries (63.6%) consider the application process to be accessible, although not without challenges, while a significant percentage of respondents (22.17%) perceive the submission stage of the funding application as relatively simple, with no major difficulties.

- How would you rate the clarity of the information provided by the programme authorities at the project submission stage regarding the project submission requirements? Please use a scale from 1 to 5

| Very good clarity (grade 5) | 27 | 61.36% |
| --- | --- | --- |
| Good clarity (grade 4) | 14 | 31.82% |
| Average clarity (grade 3) | 3 | 6.82% |
| Total | 44 | 100% |

Most respondents believe that the information provided by programme authorities was very clear and concise at the project submission stage.

- How do you rate the support provided by the Managing Authority during the project submission stage? Please use a scale from 1 to 5, where 1 represents negative appreciation and 5 positive appreciation

| Very positive (grade 5) | 35 | 79.55% |
| --- | --- | --- |
| Positive (grade 4) | 6 | 13.64% |
| Average (grade 3) | 3 | 6.82% |
| Total | 44 | 100% |

The overwhelming majority of respondents (approx. 80%) consider that the support provided by the Managing Authority during the project submission stage was very positive.

- How do you rate the use of electronic systems and tools in the interaction with the Managing Authority? Please use a scale from 1 to 5, where 1 represents a negative assessment and 5 a positive assessment

| Very positive (grade 5) | 24 | 54.55% |
| --- | --- | --- |
| Positive (grade 4) | 16 | 36.36% |
| Medium (grade 3) | 4 | 9.09% |
| Total | 44 | 100% |

The majority of respondents (90.91%) rated the use of electronic systems and tools in interaction with the Managing Authority as positive or very positive, indicating a high level of satisfaction with these digital solutions.

- How do you assess the length of time required from the moment of submitting the funding application until approval?

| The approval of the funding application took longer than expected | 5 | 11.36% |
| --- | --- | --- |
| The approval of the funding application was quicker than expected | 19 | 43.18% |
| The duration was in line with our expectations | 20 | 45.45% |
| Total | 44 | 100% |

The majority of respondents (88.63%) had a positive experience regarding the duration of the funding application approval process. According to the collected data, 45.45% considered the timeframe to be in line with their expectations, indicating a predictable and well-managed process, while 43.18% noted that the approval was faster than anticipated, reflecting improvements in procedures and a potential increase in the efficiency of the evaluation and approval process.

- What challenges did you encounter in accessing the funding opportunity?

The responses collected through the survey highlighted the following categories of challenges faced by beneficiaries in accessing funding opportunities:

- Challenges related to documentation and administrative requirements: the need to prepare a large volume of documents within a relatively short timeframe; complex and numerous requirements for substantiating the investment; the need to revise documentation due to legislative changes, etc.

- Difficulties regarding deadlines and available resources: tight deadlines for submitting funding applications, which were insufficient for obtaining the necessary supporting documents (e.g., certificates that take 3–5 days to issue and have limited validity); challenges in securing the financial resources needed for co-financing, etc.

- Challenges related to the use of the MySMIS 2021 platform: the new format required beneficiaries to go through an adaptation process.

Some respondents explicitly stated that they did not encounter difficulties in accessing funding, positively highlighting the support provided by the helpdesk service.

- What challenges did you encounter during the project preparation stage?

The responses provided in the survey highlighted the following categories of challenges encountered by beneficiaries during the project preparation phase:

- Challenges related to technical documentation and required permits: The preparation of technical documentation (e.g., DALI, technical expertise, energy audit) was frequently mentioned as a difficulty. In addition, the long issuance time for permits—especially the environmental permit—caused significant delays.

- Changes in the administrative context: Aligning the documentation with the requirements of the Applicant’s Guide across different priorities required time and constant adjustments.

- Use of the MySMIS 2021 platform: The novelty and technical difficulties of the MySMIS 2021 platform were noted by several respondents, although the Managing Authority’s technical support was appreciated.

- Time and resource management: Limited time for project preparation and the simultaneous management of multiple projects were frequently emphasized as challenges.

- Urban–rural disparities: Some responses pointed to the difficulty rural communities face in competing with cities/counties, which have better access to such projects due to their superior administrative and financial capacities.

Overall, the main challenges stem from the complexity of administrative and documentation requirements, combined with limited time and legislative unpredictability. While some responses indicated technical issues with the MySMIS 2021 platform, these were partially addressed through the technical support provided by the Managing Authority.
Time management remains a key challenge, particularly for beneficiaries implementing several projects simultaneously.

- What recommendations do you have for improving the project submission process?

Approximately half of the respondents felt that no improvements were necessary or did not provide specific recommendations, suggesting that the current process is perceived as satisfactory by a significant portion of beneficiaries.

The recommendations made by survey participants focused on the following key aspects:

- Simplification and optimization of the MySMIS platform: Reducing the complexity of the MySMIS platform, as some sections require redundant information.

- Improvement of documentation requirements: Avoiding the request for documents irrelevant to certain types of projects; replacing feasibility studies and DALI with a design note signed by the legal representative, in order to reduce the time and costs associated with documentation.

- Enhancing communication and support for beneficiaries: Organizing more meetings between the Managing Authority and beneficiaries to discuss difficulties and provide necessary clarifications.

- Extension of project submission deadlines: Recommending longer submission periods, given the complexity of the technical documentation required.

- Larger financial allocations: Some respondents mentioned that insufficient financial allocations are an issue and suggested adjusting the available budgets for calls accordingly.

- In which areas were the main administrative difficulties encountered in implementing the project? (please select one or more answers)

| I did not encounter any administrative difficulties | 30 | 68.18% |
| --- | --- | --- |
| We encountered difficulties regarding: contractual aspects and sending documentation, conducting public procurement procedures, reporting expenses, payment deadlines | 14 | 31.82% |
| Total | 44 | 100% |

According to the data collected through the survey, the majority of respondents (68.18%) did not encounter administrative difficulties during project implementation. This suggests that, overall, administrative processes were clearly understood and effectively managed. On the other hand, 31.82% of respondents reported challenges in specific areas, such as contractual issues and the submission of documentation (the most frequently mentioned), the conduct of public procurement procedures, expenditure reporting, and payment deadlines.

- Which of the following aspects do you think should be improved in the future? (please select one or more answers)

Most respondents consider that simplifying and accelerating administrative procedures are essential for improving the efficiency of project implementation, with a focus on reducing administrative burdens and improving the process of awarding contracts and making payments.

The trends and commonalities of the responses collected in the survey are presented below:

- Reducing administrative burdens in the application process and during project implementation: these are the most mentioned aspects for improvement, selected by the majority of respondents. Beneficiaries believe that simplifying administrative processes, both during the application phase and during implementation, would significantly improve the efficiency of project management.

- Contract award deadlines: a significant share of beneficiaries mentioned that contract award deadlines should be improved, suggesting a desire to speed up administrative procedures to support faster and more efficient project implementation.

- Payment deadlines: there is also significant interest in improving payment deadlines, suggesting a concern for reducing financial delays that can affect the implementation of projects.

- Information and communication initiatives: Some respondents suggested that better information and communication would be useful, possibly to ensure transparency and clarity in the project implementation process, which could reduce confusion and increase their efficiency.

- Simplifying the submission procedure: Some respondents proposed simplifying the requirements for submitting documents, including eliminating steps or documents considered additional, such as feasibility studies, approvals or documents that could be obtained after the signing of contracts.

- How would you rate the support provided by the Managing Authority in the implementation of the project? Please use a scale from 1 to 5, where 1 represents negative appreciation and 5 positive appreciation.

| very positive (grade 5) | 34 | 77.27% |
| --- | --- | --- |
| positive (grade 4) | 8 | 18.18% |
| average (grade 3) | 2 | 4.55% |
| Total | 44 | 100.00% |

The majority of beneficiaries consulted in the survey (77.27%) assessed the support provided by the Managing Authority as very positive. The data suggests that, for most of them, the support was considered efficient and valuable in the project implementation process.

- Is the project implementation carried out according to the project calendar/established deadlines?

| Yes | 40 | 90.91% |
| --- | --- | --- |
| No | 4 | 9.09% |
| Total | 44 | 100.00% |

The overwhelming majority of respondents (90.91%) believe that projects are implemented according to the established calendar and deadlines. A small percentage of respondents (9.09%) mentioned that implementation is not aligned with the established calendar, due to certain specific factors that had an impact on the implementation within the established deadlines, such as: overlapping of infrastructure works with interventions of other projects (e.g. NRRP), the need to modify projects in the technical design phase, undervaluation of investment objectives, etc.

- Is the project implementation carried out with the initially estimated human resources?

| Yes | 39 | 89.64% |
| --- | --- | --- |
| No | 5 | 11.36% |
| Total | 44 | 100% |

The responses collected through the survey indicate that the majority of respondents (89.64%) believe that project implementation is proceeding in line with initial estimates regarding human resources. However, a small proportion (11.36%) reported that the human resources used do not fully match the original estimates. These discrepancies were mainly attributed to factors such as the complexity of the project and the need to strengthen certain roles within the team.

- What are the main factors hindering the implementation of the project? (please select one or more answers)

Based on the frequency of responses provided by beneficiaries, the main factors hindering project implementation include, first and foremost, economic instability and political or regulatory changes, followed by bureaucracy and lengthy procedures required for public procurement. Difficulties with suppliers and disruptions in the supply chain were also frequently mentioned. In addition, insufficient budgets or higher-than-expected costs were identified as significant obstacles. To a lesser extent, respondents reported issues related to infrastructure works execution, rapid technological changes, lack of skills within the project team, limited material resources, or inadequate technologies.

- What are the main factors that favor the implementation of the project? (please select one or more answers)

The main elements that favor the implementation of projects include the establishment of clear and detailed objectives and effective planning, along with an adequate budget and efficient financial management. Also, a qualified team, within which there is good communication and collaboration, is another essential factor. The flexibility and adaptability of the team to changes, the availability of the necessary material and technological resources, stable economic and political conditions, reliable partnerships and suppliers, as well as the support of the local community are also important factors in supporting the successful implementation of projects .

- To what extent do you believe the project will achieve its expected results?

| The project will achieve 100% of the expected results | 38 | 88.37% |
| --- | --- | --- |
| The project will achieve the expected results in a proportion of 80%-99% | 4 | 9.30% |
| The project will exceed the expected results | 1 | 2.33% |
| Total | 43 | 100.00% |

Regarding the achievement of expected results, the majority of respondents (88.37%) believe that the project will fully reach its objectives. A smaller share (9.30%) estimates that the project will achieve between 80% and 99% of its intended results, while only 2.33% of respondents expect the project to exceed the anticipated outcomes.

- What are the main risks that you consider may affect the implementation of the project?

The risks that could affect project implementation are diverse and are related to several essential areas. Among these, risks associated with public procurement procedures include delays caused by challenges to the procedures, legislative changes that may lead to increased costs, and difficulties in conducting procurements, such as the cancellation of procedures due to non-compliant offers. Additionally, the lack of qualified economic operators can result in delays in signing procurement contracts.

Financial risks are also a significant concern, with potential blockages in payment flows from the MA and the risk that economic instability may lead to price increases beyond the approved budget.

Legislative changes can also affect the project's execution and the allocation of financial resources, while challenges during the service contracting phase can cause unforeseen delays.

Furthermore, there are risks related to the project team, such as dependence on external experts, whose involvement is more difficult to manage.

- As a beneficiary of the Regional Programme, how do you evaluate this funding opportunity, from the perspective of the benefits/results obtained so far?

| very positive (grade 5) | 37 | 86.05% |
| --- | --- | --- |
| positive (grade 4) | 5 | 11.63% |
| average (grade 3) | 1 | 2.33% |
| Total | 43 | 100.00% |

The majority of respondents (86.05%) evaluated the funding opportunity offered by the South-West Oltenia Regional Programme very positively, awarding the highest rating (5), while 11.63% gave a positive rating (4). Only one respondent (2.33%) considered the impact of the funding to be average, awarding a score of 3. Overall, the results of the survey indicate a high level of satisfaction among the beneficiaries of the programme.

- To what extent would you have implemented the project without EU/ERDF funding?

| I would not have implemented the project at all | 35 | 81.40% |
| --- | --- | --- |
| I would have implemented the project with my own resources, but with fewer expected results | 4 | 9.30% |
| I would have implemented the project with my own resources, but over a longer period of time | 3 | 6.98% |
| I would have implemented the project anyway without the funding under the SW RP | 1 | 2.33% |
| Total | 44 | 100% |

The results of the analysis indicate that, in the absence of EU/ERDF funding, a significant proportion of beneficiaries (81.40%) would not have had the capacity to implement their projects. 9.30% of respondents claim they would have been able to carry out the projects using their own resources, but with results lower than initially estimated, while 6.98% believe implementation would have been possible, but over a longer period of time. Only 2.33% of the beneficiaries participating in the survey stated that they would have completed the projects independently of the funding provided by the South-West Oltenia Regional Programme.

- Do you intend to apply for similar financial support (grant support) in the future, if available?

All respondents stated that they intend to apply for non-reimbursable financial support in the future, if such an opportunity becomes available. This result underlines the high interest of beneficiaries in continuing to access European funds, highlighting the importance of this type of financing in supporting development projects.

- What improvements would you suggest for the next stages of implementation and management of projects funded by SW Oltenia RP? (e.g., with reference to the application process, selection criteria, etc.)

To improve future implementation and management stages of projects funded through the South-West Oltenia Regional Programme, beneficiaries have made several suggestions. Key proposals include reducing the volume of required documentation, simplifying bureaucratic procedures, and improving the MySMIS 2021 platform, including the development of a more intuitive interface that is interoperable with other information systems (e.g., SEAP, ANAF).

Additionally, some respondents emphasized the need to eliminate certain administrative requirements, such as feasibility studies, DALI, and specific approvals during the application and evaluation stages, suggesting that a detailed justification note could serve the same purpose for evaluators.

Regarding selection criteria, it was proposed to grant additional points to beneficiaries who have previously implemented projects efficiently and on time.

To support implementation, beneficiaries consider it useful to create a communication module where they can request assistance for specific issues encountered during project execution. These measures could contribute to enhancing the efficiency and accessibility of the programme in the upcoming stages.

- Are there any new development needs that you believe should receive financial support? (Please specify any needs that were not initially identified within the programme)

Analyzing the additional needs reported by beneficiaries, it can be observed that many of these are already addressed within the South-West Oltenia Regional Programme 2021-2027. For example, support for energy efficiency in public buildings, development of educational and cultural infrastructure, rehabilitation of cultural heritage, and modernization of urban infrastructure are funding directions included in the programme. Additionally, the development of business infrastructure and support for tourism are among the programme's investment priorities.

However, there are certain needs that are either insufficiently covered or require adjustments to eligibility criteria to facilitate access to funding, particularly in rural or marginalized areas. Therefore, a potential improvement to the programme could involve the flexibilization of certain funding conditions and simplification of administrative procedures, aspects frequently mentioned by respondents.