# Case Study Report

Priority 3: Energy Efficiency and Green Infrastructure

Project: SMIS 300142 – Rehabilitation works to improve energy efficiency at Dormitories 1 and 2

Beneficiary: University of Medicine and Pharmacy of Craiova

## Project preparation

  - Context and existing framework (needs to be addressed)

The project addresses the need to improve the energy performance of buildings owned by the University of Medicine and Pharmacy of Craiova, in light of the significant increase in the institution's electricity expenditure.
The implementation period of the project is 46 months, from 14th of February 2024 to 31st of December 2026.

  - Project design and submission (internal objectives, alignment with national and regional strategies, relationship with the MA during the submission phase, with reference to the support and information provided to potential beneficiaries)

Regarding project preparation, the beneficiary considers that the structure of the call for projects was fairly clear; however, challenges arose due to European regulations, where the beneficiary would prefer greater flexibility.

The project was prepared with the support of a consultancy firm with prior experience in the Regional Operational Programme and other funding programmes, which ensured a smooth drafting process. According to discussions with the consultant, the documentation required was extensive, involving numerous regulations, standards, and norms—areas that had not been heavily emphasized in previous calls—along with the obligation to comply with the DNSH principle.

Additionally, the MySMIS application is not yet fully functional—specifically, the Communication module is missing, which means communication is currently carried out via email. The beneficiary’s manual is also not fully adapted, with two different versions currently in circulation.

The requirements in the guidance, particularly the mandatory 60% reduction target, were seen as rather strict, posing a challenge to achieve through the technical documentation.

Nevertheless, the relationship with the Managing Authority facilitated the project preparation and submission stages. Communication with the SW Oltenia Regional Development Agency has been very good, with designated contact persons available in all departments.

The project contributes to the following national and regional strategies:

- National Energy Efficiency Action Plan III

- Romania’s National Climate Change Strategy 2013–2020

- South-West Regional Development Plan

Eligibility criteria and partnership formation:

The project was not developed within a partnership.

As for eligibility criteria, no issues were encountered; however, it was challenging to meet the minimum scoring threshold (investment cost-benefit ratio, and the mandatory 60% energy reduction target). There is a possibility that the amount of ineligible expenditure will increase, given the significant rise in costs.

Complementarity:
The funding provided through the SW RP was launched shortly after another financing opportunity under the National Recovery and Resilience Plan – Component 5, Renovation Wave. However, under that scheme, only buildings owned by the central public sector were eligible.

2. Project implementation

  - Internal management and governance

Compared to the funding provided under the 2014–2020 ROP, there are no major differences in the current programming period. However, the SW Oltenia RP can be considered more efficient. The beneficiary's previous experience working with the RDA as an Intermediate Body has facilitated current interactions.

  - Main obstacles (external and internal) and factors facilitating project implementation

The main obstacles stem from the use of the MySMIS application, which is still not fully operational—specifically, the Communication module is missing, requiring exchanges to be carried out via email.
The main factor facilitating implementation is the effective communication with the MA.

3. Project results

  - Main activities

According to the information provided in the funding application, the main activities of the project include:

- Preparatory activities

- Design and technical assistance services

- Procurement of consultancy services

- Information and publicity activities

- Construction works

- Site supervision

- Energy certification

The financing contract was signed in February 2024, meaning that nine months of implementation have passed. There have been slight delays, as the beneficiary was required to repeat the design procurement process. Due to the submission of non-compliant bids, the procedure had to be relaunched. Consequently, the design contract was signed at the end of September 2024, and it is estimated that the technical project and building permit will be obtained by January 2025.

Based on current estimates, despite minor delays, the beneficiary believes the project will be completed within the implementation timeframe (35 months in total).

To date, three progress reports and one reimbursement request for expenses incurred prior to the signing of the contract have been submitted.

There has been an addendum to amend the monitoring plan, as well as a unilateral modification by the Regional Development Agency, which introduced specific regulations that had to be incorporated into the financing contract.

The beneficiary is confident that the objectives set out in the project will be fully achieved.

  - Results

The following project indicators have been proposed:

- RCO19 – Public buildings with improved energy performance (square meters):
Less developed region – Target: 7,827.36 m²

- RCR29 – Estimated greenhouse gas emissions (tons of CO₂ equivalent/year):
Less developed region – Target: 110.13 tons CO₂ eq/year

- RCR26 – Annual primary energy consumption (from residential buildings, public buildings, enterprises, etc.) (MWh/year): Less developed region – Target: 891.16 MWh/year

Potrivit interviului cu beneficiarul, printre riscurile care ar putea afecta atingerea obiectivelor proiectului, cel mai important este reprezentat de creșterea prețurilor.

Alte riscuri, identificate prin proiect, sunt reprezentate de: întârzieri în rambursarea cheltuielilor; aplicarea de corecții/penalități financiare; proiectarea defectuoasă a activităților cu impact asupra implementării proiectului; prelungirea implementării proiectului, ca urmare a nerespectării termenelor de finalizare a activităților proiectului; neatingerea indicatorilor proiectului, ca urmare a supraestimării acestora și/sau a necorelării acestora cu activitățile și scopul proiectului; condiții meteorologice nefavorabile pentru realizarea lucrărilor de construcții.

Beneficiarul consideră că aceleași rezultate ca cele obținute din implementarea proiectului nu ar putea fi obținute cu costuri mai mici.

Potrivit informațiilor furnizate prin cererea de finanțare, proiectul va contribui la adoptarea de noi tehnologii, prin instalarea unor sisteme alternative de producere a energiei electrice, modernizarea sistemelor de climatizare, ventilare naturală și ventilare mecanică, modernizarea instalațiilor de iluminat și lucrări conexe acestora.

Additional output indicators:

- Number of buildings benefiting from energy efficiency improvement measures
Less developed region – Reported value: 0.00 units – Target: 1.00 unit

- Estimated annual reduction in greenhouse gas emissions
Less developed region – Reported value: 0.00 kg CO₂ equivalent/m²/year – Target: 14.07 kg CO₂ equivalent/m²/year

- Primary energy consumption from renewable sources at project completion
Less developed region – Reported value: 0.00 kWh/m²/year – Target: 63.90 kWh/m²/year

- Reduction in total primary energy consumption
Less developed region – Reported value: 0.00 kWh/m²/year – Target: 113.85 kWh/m²/year

- Reduction in specific annual final energy consumption for heating
Less developed region – Reported value: 0.00 kWh/m²/year – Target: 140,236.11 kWh/m²/year

It is currently too early to assess the achievement of the objectives and indicators; however, by the end of the project, they are expected to be met.

According to the beneficiary interview, the most significant risk that could impact the achievement of project objectives is the increase in prices.

Other identified risks, as outlined in the project, include: delays in the reimbursement of expenditures; application of financial corrections/penalties; inadequate design of activities impacting project implementation; extension of the implementation period due to missed deadlines; failure to meet project indicators, either due to overestimation or lack of alignment with project activities and objectives; unfavorable weather conditions affecting construction works.

The beneficiary believes that the same results could not be achieved at a lower cost.

According to the information provided in the funding application, the project will contribute to the adoption of new technologies through the installation of alternative electricity generation systems, modernization of HVAC systems (heating, ventilation – both natural and mechanical), modernization of lighting installations, associated construction works.

  - Unintended effects

Increase in attractiveness among students as a result of thermal rehabilitation of the dormitories.

4. Theory of change for project code SMIS 300142