## Annex 10.8 Benchmarking analysis

### External benchmarking analysis

External benchmarking analysis allows for a comparative overview of the programme in relation to the following aspects:

- Implementation on planned, decided and spent amount,

- Contribution to the European Pillar of Social Rights,

- Contribution to the PNIEC objectives / dimensions.

#### Comparative overview on programme implementation

The DG REGIO Open Cohesion Data platform at the date of 5 February 2025 provides data up to 31/10/2024 for all the EU Member States on three main variables

- Planned allocation: Total budget of the programme. This refers to the total allocation (national and EU resources) at the latest programme update available.

- Decided allocation: Financial resources allocated to selected projects, which represents a proxy of the project pipeline, namely total costs of selected operations.

- Spent allocation: Expenditure reported by the selected projects, notably total eligible costs which have been declared by beneficiaries.

Despite not being updated to the situation at 31/12/2024, which represents the reference cut-off date of the Mid-Term Review, however, this data offers an overview at the EU level, in particular among EU and Romanian less developed regions, such as South West Oltenia.

The benchmarking analysis examines the relative positioning at the end of October 2024 of the South West Oltenia RP in comparison with other regional programmes in less developed regions and in other Member States for the Specific Objectives which have been selected by the South West Oltenia programme: RSO1.1, 1.2, 1.3, 1.4, 2.1, 2.7, 2.8, 3.2, 4.2, 5.1 and 5.2.

This analysis uses the following indexes.

- Index 1 (performance in selecting operations)=Decided total amount (selected operations)Planned total amount (total programme budget)

- Index 2 (performance on the expenditures)=Spent total amount (expenditure reported by selected projects)Decided total amount (selected operations)

The analysis, summarized in the table below, allows the following findings:

- The performance of the entire South West Oltenia programme in selecting operations is better than the average situation of other less developed regions in Romanian and in all EU Member States. However, this performance has not yet produced tangible consequences on expenditure performance. Only for RSO 2.1 (energy efficiency), the South West Oltenia RP performance on spent resources is in line with Romanian less developed regions but worse than EU Member State less developed regions.

- At the level of specific objectives, the most performant ones cover energy efficiency, nature protection and biodiversity, sustainable transport and education.

Tabel no. 1 Overview of the South West Oltenia performance against other programmes from RO and EU less developed regions (October 2024)

|  | Index 1 (performance in selecting operations) | Index 2 (performance in spending) |
| --- | --- | --- |
| RSO1.1 Enhancing research and innovation |  | Not possible to assess |
| RSO1.2 Reaping the benefits of digitisation |  | Not possible to assess |
| RSO1.3 Growth and competitiveness of SMEs |  |  |
| RSO1.4 Skills for smart specialisation and transition |  |  |
| RSO2.1 Energy efficiency |  |  |
| RSO2.7 Nature protection and biodiversity |  |  |
| RSO2.8 Sustainable urban mobility |  |  |
| RSO3.2 Sustainable transport |  |  |
| RSO4.2 Education infrastructure |  |  |
| RSO5.1 Integrated development in urban areas |  |  |
| RSO5.2 Integrated development in rural and coastal areas |  |  |
| Total RSOs (technical assistance excluded) |  |  |

Notes

|  | The South West Oltenia programme performance at the end of October 2024 is worse than the performance of ERDF programmes in less developed Romanian and EU Member States. |
| --- | --- |
|  | The South West Oltenia programme performance at the end of October 2024 is between the other two groups (either better than the performance of ERDF programmes in less developed Romanian regions and worse than the performance of EU Member States programmes in less developed regions or viceversa). |
|  | The South West Oltenia programme performance at the end of October 2024 is better than the performance of ERDF programmes in less developed Romanian and EU Member States. |

‘Not possible to assess’ where there is no progress at all in the South West Oltenia programme according to Open Data Cohesion Platform

#### Comparative outlook on programme contribution to the progress of the European Pillar of Social Rights

According to the annexes to the European Commission Communication for the European Pillar of Social Rights action plan :

- The category “Equal opportunities and access to the labor market” is associated with the Sustainable Development Goals (SDG)s 4. Quality education  5. Gender equality and  10. Reduced inequalities;

- The category “Fair working conditions” correspond to the SDG 8 Decent work and economic growth;

- The category “Social protection and inclusion” is linked with SDG 1 No poverty and  SDG 3. Good health and well-being.

Based on Annex I CPR intervention fields and Open Data Cohesion Platform, it is possible to highlight the contribution of South West Oltenia Programme to the aforementioned SDGs and related categories. This analysis is to be seen as a complementary tool to the qualitative review already conducted for the mid term evaluation report. The added value of this analysis is to offer a comparative view between the South Vest Oltenia RP and other programmes, while qualitative analysis explains the actions supported as well as the selection criteria and relevant element on programme indicators. The South West Oltenia Programme performance is compared with ERDF Romanian programmes (South West Oltenia included) in less developed regions and ERDF EU programmes in less developed regions (South West Oltenia included) based on October 2024 data from Open data Cohesion Platform.

South West Oltenia RP shows a higher potential than both the ERDF Romanian and EU programmes in less developed regions to contribute to EPSR principles, with 34% of its total planned financial allocation which is expected to contribute to EPSR, while this value is 26% in Romanian ERDF programmes of less developed regions and 24% in EU Member States ERDF programmes of less developed regions.

Programme allocation shows a higher potential contribution with a focus on:

- SDG 1 (no poverty) with investments in social infrastructure for social inclusion in RSO 5.1,

- SDG 4 Quality of education through RSO 4.2,

- SDG 8 Decent work and economic growth through RSO 1.3, RSO 1.4, RSO 5.1 and 5.2.

In spite of this potential of financial contribution, the Programme has a lower capacity to decide and spend allocated resources by October 2024. Indeed, the programme implementation in terms of decided and spent amount is lower than the other two groups of programmes considered.

Also considering the latest data available in December 2024, the most significant margins of improvement in terms of disclosing the programme financial potential to contribute to EPSR pillars regard RSO 5.1, for which there is no implementation for the intervention field 127 even at the end of December 2024.

For the SDG 4 Quality education, there has been acceleration for infrastructure investments for primary and secondary education and tertiary education while early childhood education and care still lag behind at the end of 2024.

In the case of SG 8 Decent work and economic growth, while the implementation of RSO 1.3, RSO 5.1 and 5.2 (cultural and tourism sector) has started, RSO 1.4 requires acceleration.

Tabel no. 2 Overview of the South West Oltenia contribution to the European Pillar of Social Rights – Values are in EUR

|  | South West Oltenia |  |  | Programmes from less developed regions in Romania |  |  | Programmes from less developed regions in EU |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Total Planned | Total decided | Total spending | Total Planned | Total decided | Total spending | Total Planned | Total decided | Total spending |
| SDG 1 No poverty | 1194614.12 |  |  | 292440193.4 | 75831529.83 | 556469.66 | 4501550386 | 712210922 | 37120502.47 |
| SDG 3 Good Health and wellbeing |  |  |  | 2939251988 | 1907634223 | 4417619.09 | 8445624730 | 3240570970 | 83191272.43 |
| SDG 4 Quality education | 96944771.66 | 77889709.48 | 492547.93 | 711642695.5 | 327521544.4 | 8507800.02 | 6143455184 | 1425493378 | 125304746 |
| SDG 8 Decent work and economic growth | 313847844 | 46947262.35 |  | 2279198379 | 314659908.4 | 8967100.7 | 26594844021 | 9252010123 | 1314784222 |
| Total value of the programme(s) | 1213553688 | 688085496.8 | 8462922.23 | 23653070190 | 12436498330 | 520591001.1 |  |  |  |
| Share of SDGs related to EPSR | 34% | 18% | 6% | 26% | 21% | 4% | 23% | 27% | 35% |
| General assessment | South West Oltenia RP has a higher potential than other ERDF Romanian and EU programmes in less developed regions to contribute to EPSR principles, but lower capacity in terms of the amounts allocated through calls launched and expenses, by reference to October 2024 |  |  |  |  |  |  |  |  |

Source: own processing based on data provided by the Open Data Cohesion Platform (Octombrie 2024)

Tabel no. 3 Overview of the South West Oltenia performance for the European Pillar of Social Rights for selected intervention fields (October and December 2024) ) – Values are in EUR

|  | Situation at 31 October 2024 |  |  | Situation at 31 December 2024 |  |
| --- | --- | --- | --- | --- | --- |
| Intervention field | Sum of Total Planned (Oct. 2024) | Sum of Total decided (Oct. 2024) | Sum of Total spending (Oct.2024) | Eligible costs (Dec. 2024) | Spending (Dec. 2024) |
| SDG 1 No poverty | 1194614.12 | 0 | 0 | 0 | 0 |
| 127 | 1194614.12 | 0 | 0 | 0 | 0 |
| SDG 4 Quality education | 96944771.66 | 77,889,709.48 | 492,547.93 | 77,861,536.78 | 1,540,555.86 |
| 121 | 12000000 | 4091818.46 | 0 | 4,090,338.45 | 0 |
| 122 | 56522823.33 | 62744096.39 | 492547.93 | 64,046,534.10 | 624560.79 |
| 123 | 28421948.33 | 11053794.63 | 0 | 9,724,664.23 | 915995.07 |
| SDG 8 Decent work and economic growth | 313847844 | 46,947,262.35 | 0 | 96,826,331.83 | 1,031,344.54 |
| 21 | 154321176.5 | 0 | 0 | 56,045,105.21 | 0 |
| 23 | 1470588.24 | 0 | 0 | - | 0 |
| 25 | 9411764.71 | 8616259.28 | 0 | 3,700,459.56 | 0 |
| 165 | 67716276.66 | 10951031.46 | 0 | 6,589,058.38 | 294371.68 |
| 166 | 80928037.88 | 27379971.61 | 0 | 30,491,708.68 | 736972.86 |

Source: own processing based on data provided by the Open Data Cohesion Platform (October 2024) and data reported in the SFC (December 2024)

#### Comparative outlook on programme contribution to the PNIESC dimensions and objectives

The Integrated National Plan for Energy and Climate Change is structured around five dimensions, which follow the key dimensions assumed at European level, after the signing of the Paris Agreement, namely: i. decarbonization; ii. energy efficiency; iii. energy security; iv. internal energy market and v. research, innovation and competitiveness.

Before starting with a specific review on the South West Oltenia RP contribution to PNIESC objectives and dimensions, analysis of Annex I CPR intervention fields at the end of October 2024 (latest data available on Cohesion data platform) offer a comparative overview of three indexes:

- Share of EU climate amount Planned EU climate amount Planned EU amount (EU programme budget)

- Performance of decided EU climate amount Decided EU climate amountPlanned EU climate amount

- Performance of spent EU climate amount Spent EU climate amountDecided EU climate amount

These indexes do not offer a precise and specific contribution to PNIESC objectives but they allow for a highlight of the programme's performance in terms of climate objectives.

As show in the following table, it is clear that South West Oltenia programme has a similar focus on planning for climate change to other Romanian and EU ERDF programmes in less developed regions, while having a lower capacity to spend. Nonetheless, it is interesting to notice that the performance in terms of selecting operations is much better, this is due to the very good performance of RSO 2.1, which decided for almost the total planned EU amount at the end of October 2024.

Tabel no. 4 Overview of EU climate amount performance (October 2024)

|  | Planned EU climate amount Planned EU amount | Decided EU climate amountPlanned EU climate amount | Spent EU climate amountDecided EU climate amount |
| --- | --- | --- | --- |
| SW Oltenia RP | 30,1% | 67,5% | 0,8% |
| Romanian ERDF programmes in less developed regions | 30,3% | 47,6% | 2,5% |
| ERDF programmes in less developed regions (EU) | 32,7% | 27,5% | 6,4% |

Source: Own elaborations based on Cohesion data platform (October 2024)

Data in December 2024 completes the previous overview with more specific elements and updates which can be useful to give a more quantitative dimension to the programme contribution in the progress to PNIESC objectives. As for EPSR, this analysis is to be seen as a complementary tool to the qualitative review already conducted for the evaluation report. Overall, there is no progress of RSO 1.1 and 1.3 to the dimensions of PNIESC: i. decarbonization and v. research, innovation and competitiveness. Meanwhile, the RSO 2.1 shows a strong contribution (selected operations and spent amount) to i. decarbonization, ii. energy efficiency, iii. energy security. RSO 2.8 contributes substantially to the decarbonisation of the local public transport services (decided and spent amount).

Tabel no. 5 Overview of the financial allocation for climate objectives at the level of the PR SV Oltenia (December 2024) – Values ​​are expressed in euros

| Intervention field | RSO | Total planned | Total decided (eligible costs of selected operations) | Total expenditure declared by beneficiaries | PNIESC dimensions |
| --- | --- | --- | --- | --- | --- |
| 029 Low-carbon development and innovation processes, technology transfer and cooperation | 1.1 | 11818823,53 |  |  | i. decarbonisation v. research, innovation and competitiveness |
| 030 Circular economy, development and innovation processes, technology transfer + cooperation | 1.1 | 2352941,18 |  |  | v. research, innovation and competitiveness |
| 040 Energy efficiency in enterprises - deep renovation | 1.3 | 3970588,24 |  |  | v. research, innovation and competitiveness |
| 042 Energy efficiency in homes - deep renovation | 2.1 | 40000000,04 |  |  | i. decarbonisation ii. energy efficiency iii. energy security |
| 045 Energy efficiency in public infrastructure - deep renovation | 2.1 | 151603529,6 | 151427598,7 | 2683260,33 | i. decarbonisation ii. energy efficiency iii. energy security |
| 079 Nature and biodiversity protection | 2.7 | 87868235.39 | 43371983,78 | 0 | More indirect impact on topics related to nature and biodiversity than climate change even if climate tracking attributes a financial value of this intervention field |
| 081 Clean urban transport infrastructures | 2.8 | 40576470.73 | 37142248,1 | 5169095,43 | i. decarbonisation |
| 082 Clean urban transport rolling stock |  | 34705882.47 | 13260817,84 | 0 | i. decarbonisation |
| 083 Infrastructure for cyclists |  | 23529411.84 | 0 | 0 | i. decarbonisation |
| 085 Digitalization and urban transport – reducing GHG emissions |  | 9705882.39 | 9123091,31 | 396154,96 | i. decarbonisation |
| 086 Alternative fuels infrastructure |  | 7411764.73 | 0 | 0 | i. decarbonisation |

Source: own processing based on data provided by SW RP MA (December 2024)

## Internal benchmarking between specific objectives

Table 2 of the data transmitted by the MA of SW RP to SFC referring to 31.12.2024 shows the relative performance of each specific objective of the programme and priorities. Overall, it is interesting to note that there is no substantial variation between the entire total allocation per priority and the eligible costs, except in the case of Priority 5 in which the eligible value of selected operations surpassed the financial allocation. Moreover within P1 and P3, there are substantial differences between specific objectives, however, more performing specific objectives have not surpassed in terms of total eligible value of selected operations their financial allocation. All these elements can be considered in the perspective of elaborating suggestions and conclusions on allocation of the flexibility amount.

Tabel no. 6 SFC data extract (December 2024)

| Priority | Specific objective | Total financial allocations by fund and national contribution (EUR) | Total eligible cost of selected operations (in EUR) | Contribution from the Funds to selected operations (in EUR) | Percentage of total financial allocation covered by selected operations (%) | Total eligible expenditure declared by beneficiaries | Percentage of the total financial allocation covered by eligible expenditure declared by beneficiaries (%) | Number of selected operations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| P1 | RSO1.1 | 60642352,94 | 0 | 0 | 0,00% | 0 | 0,00% | 0 |
| P1 | RSO1.3 | 181207058,82 | 59745564,77 | 37931074,79 | 32,97% | 0 | 0,00% | 52 |
| P1 | RSO1.4 | 1470588,24 | 0 | 0 | 0,00% | 0 | 0,00% | 0 |
| P2 | RSO1.2 | 34487136,00 | 2362679,62 | 2008277,64 | 6,85% | 28599,22 | 0,08% | 4 |
| P3 | RSO2.1 | 191603529,61 | 151427598,7 | 128415124,8 | 79,03% | 2683260,34 | 1,40% | 76 |
| P3 | RSO2.7 | 87868235,39 | 43371983,78 | 36866186,17 | 49,36% | 0 | 0,00% | 9 |
| P4 | RSO2.8 | 119430211,00 | 59526157,25 | 50597233,57 | 49,84% | 5565250,39 | 4,66% | 16 |
| P5 | RSO3.2 | 135371986,00 | 252667154,5 | 92636315 | 186,65% | 5217293,87 | 3,85% | 9 |
| P6 | RSO4.2 | 100278105,00 | 77861536,78 | 46716922,2 | 77,65% | 1540555,85 | 1,54% | 44 |
| P7 | RSO5.1 | 216887694,72 | 112579297,5 | 95470932,06 | 51,91% | 662258,01 | 0,31% | 33 |
| P7 | RSO5.2 | 35483261,28 | 8092236,84 | 6774365,97 | 22,81% | 636145,43 | 1,79% | 4 |
| P8 |  | 48823529,00 | 14844900,75 | 10845684,49 | 30,41% | 7238682,46 | 14,83% | 2 |
| Total |  | 1213553688 | 782479110,4 | 508262116,6 | 64,48% | 23572045,57 | 1,94% | 249 |

Source: Own elaborations based on SFC data on 31.12.2024

https://eur-lex.europa.eu/resource.html?uri=cellar:b7c08d86-7cd5-11eb-9ac9-01aa75ed71a1.0001.02/DOC_2&format=PDF